## Sheet1
WDCO Dashboard
MILESTONE | TARGET | Update from partner reports | WDCO Commentary and questions | Update from the Partnership Board
Block D | Early Spring 2026 | Hackney plan to agree a lease with Millco by the end of February 2026. This agreed lease will then be signed and completed when Millco enters into its own arrangements with end users, and the building opens in early Spring 2026. (Update from LBH in December) | Is it Asset Management or Legal that is holding this up, and can we speak directly to that team? What guarantee do we have that the sublease will be signed in February? Will be raised at the Partnership Board on 11th December.
West Reservoir | 2026-04-01 | The West Reservoir works (Update from LBH in December) The project has made good progress. Completion is expected in Spring 2026: 1. Work to the existing building is nearing completion including new workshops, changing rooms and showers. 2. Work to the new cafe building has now started 3. The bridges (e.g. the bridge connecting Woodberry Down to the Reservoir) will be installed in the new year, as well as all planting. 4. A local resident has been recruited as a paid trainee on site (funded by Blakedown the contractor). The contractor is also funding an open day for young people, and organising work experience for students aged 14-17. | Email sent to Ian and Gareth on 8th December: It would be really helpful to have a full timeline for all elements of the project, including start and completion dates for each the below works. 1. Work to the existing building is nearing completion including new workshops, changing rooms and showers. 2. Work to the new cafe building has now started 3. The bridges (e.g. the bridge connecting Woodberry Down to the Reservoir) will be installed in the new year, as well as all planting.
Split household (LLP) | Summer 2026 | At the November Board meeting, Hackney reported that the Split Household Policy is currently live and will be reviewed in the summer of 2026. The review will now happen alongside a review of the borough wide allocations policy. The scope of this review has yet to be agreed. (Update from LBH in December) | Chair has sent an email to Cllr Nicholson - awaiting response - Will be raised at the Partnership Board on 11th December. 1. When WDCO should expect response to their email asking for a) confirm when the summary of recent legal advice will be provided; b) share a summary or copy of the original QC opinion on the Local Lettings Policy; 2. Hackney to provide clarification on the scope of the Split Household review, due to begin in summer 2026.(action from November Board) 3. Obtaining written confirmation from Hackney on the data they have submitted to BH for the detailed design of Phase 5, specifically whether the figures assume that residents in later phases being offered Phase 5 will have the option of the split-house arrangement. If this is the case, fewer larger homes will need to be delivered. However, if that policy changes following the review, what would be the implications for Phase 5?
Phase 5 Phase 5: Vacant Possession and Decant Strategy |  | The timescale to bring Phase 5 ‘in phase’ is dependent on developing a decant strategy in more detail, and the regeneration team is working closely with Berkeley on this. The resultant ‘decant strategy’ will be shared with WDCO in due course. | 1. How will the Council manage the increased risk of objections to the CPO due to the lack of available shared equity homes? 2. Could we get a clear timeline of when the decant strategy will be shared with the Board and when it's due to go to cabinet. Will be raised at the Partnership Board on 11th December.